## Title Page
Project Name
Project Risk Assessment Report
Prepared by: | University of Calgary
Information Technologies
Issue date: | dd Month year
Version: | 0

## Document History
< The revision history log maintains a record of changes to this document, along with the associated revision number and date. The Communication of Change column is intended to document how the change was communicated to all stakeholders. >
Document History
Revision Number | Date | Description of Changes | Author / Editor | Communication of Change
| dd-mm-yy | Initial drafts
Document Owner
Name | Title | Organization | E-mail | Tel.
Document Distribution
Name | Type of Copy | Title | Organization | E-mail | Tel.

## Introduction
Instructions
1) Answer the questions on the numbered tabs 1-10 by selecting a pulldown choice in the pale blue column "C"
(the Severity column "D" will be calculated automatically)
2) Optionally, enter your own project specific risks on tab "11 - Project Specific"
3) Review your project risk profile and overall project risk score on tab "12 - Risk Calculation"

## 1. Size and Scope
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
| Size and Scope | Value | Severity
1.1 | Current estimated total size of the development in mandays | <Choose Value> | #REF!
1.2 | Total scheduled duration of project in months | <Choose Value> | #REF!
1.3 | Is the project duration too short? i.e. too many staff with insufficient time | <Choose Value> | #REF!
1.4 | Is the project duration too long with a risk of disruption from loss of or changes in staff? | <Choose Value> | #REF!
1.5 | The partitioning of the whole development into a number of sub-projects is | <Choose Value> | #REF!
1.6 | Now that the project has been partitioned compare the original timescale with the new one | <Choose Value> | #REF!
1.7 | What is the make up of the team in terms of staff and others? | <Choose Value> | #REF!
1.8 | How many systems will interface with this system? | <Choose Value> | #REF!
1.9 | Has responsibility for defining the interfaces been allocated? | <Choose Value> | #REF!
1.10 | How many people will be working full time on the project at its peak? | <Choose Value> | #REF!
Size and Scope Total |  |  | #REF!

## 2. IT Tools & Methods
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
2 | IT Tools & Methods | Value | Severity
2.1 | Will the project require changes to the normal procedures and standards for system developments? | <Choose Value> | #REF!
2.2 | Will the project require changes to guidelines for control and security? | <Choose Value> | #REF!
2.3 | How reliable are estimates for the volumes, frequencies, times and types of transactions etc.? | <Choose Value> | #REF!
2.4 | Has the project been given a clear definition of its priorities and sufficient support and backing from the client's IT department? | <Choose Value> | #REF!
2.5 | Will the project use a methodology familiar to the majority of the project team? | <Choose Value> | #REF!
2.6 | How satisfactory is the access to computer equipment necessary for project staff's work and what are the response times like? | <Choose Value> | #REF!
2.7 | Will the project use standard methods for project management? | <Choose Value> | #REF!
2.8 | Will the project use standard methods for testing and approval? | <Choose Value> | #REF!
2.9 | What is the extent of relative IT experience amongst the project's IT staff? | <Choose Value> | #REF!
IT Tools and Methods |  |  | #REF!

## 3. Project Organization
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
3 | Project Organization | Value | Severity
3.1 | What percentage of the development team are assigned less than full time to the project? | <Choose Value> | #REF!
3.2 | How would you rate the balance between IT personnel and other staff? | <Choose Value> | #REF!
3.3 | Has the project staff the experience and the time to cope with areas such as administration and operating procedures? | <Choose Value> | #REF!
3.4 | To what extent will end users participate in the project activities? | <Choose Value> | #REF!
3.5 | What is the extent of the project staff's knowledge of the application? | <Choose Value> | #REF!
3.6 | Is there a possibility that the project could be affected by a high turnover of personnel? | <Choose Value> | #REF!
3.7 | Will personnel not directly involved in the project be examining it at critical stages eg. members of the PMO or QA team? | <Choose Value> | #REF!
3.8 | Is there a possibility that the project could be affected by poor motivation or a lack of cooperation amongst personnel because of the environment or interpersonal relations? | <Choose Value> | #REF!
Project Organization Total |  |  | #REF!

## 4. Project Management
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
4 | Project Management | Value | Severity
4.1 | What is the extent of project management's experience of systems in this business area? | <Choose Value> | #REF!
4.2 | What is the extent of the project management's knowledge of data processing? | <Choose Value> | #REF!
4.3 | What is the extent of the project management's experience of projects of a similar nature and size? | <Choose Value> | #REF!
4.4 | Have change control procedures been agreed and are they actually being used by the team and client staff? | <Choose Value> | #REF!
4.5 | What is the extent of the project management's experience of the technical environment? | <Choose Value> | #REF!
4.6 | What is the extent of the project management's familiarity with the activities and practices of the client? | <Choose Value> | #REF!
4.7 | Does the structure of the project management permit sound commercial decisions to be made? | <Choose Value> | #REF!
Project Management |  |  | #REF!

## 5. Project Op Cond
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
5 | The Project's Operating conditions | Value | Severity
5.1 | What is the probability that the priority of the project will be reduced by the client during its life? | <Choose Value> | #REF!
5.2 | Are there organisational guidelines or regulations governing internal security and safety or if not have they been detailed in the plan of approach by the project management? | <Choose Value> | #REF!
5.3 | How complex are the rules and regulations governing the project eg. legislation? | <Choose Value> | #REF!
5.4 | Will more than normal reporting information be required during the project? | <Choose Value> | #REF!
The Project's Operating Conditions Total |  |  | #REF!

## 6. Business Process
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
6 | Business Process | Value | Severity
6.1 | To what extent has the new system already been automated? | <Choose Value> | #REF!
6.2 | To what extent will there be changes to specific manual processes? | <Choose Value> | #REF!
6.3 | To what extent will there be changes to current overall administrative procedures? | <Choose Value> | #REF!
6.4 | Will the system users be exposed to new equipment possibly requiring them to be trained? | <Choose Value> | #REF!
6.5 | To what extent will the user need to be trained for them to fully utilise the new system? | <Choose Value> | #REF!
6.6 | What experience do end users have of data processing? | <Choose Value> | #REF!
6.7 | How many new working procedures or techniques will be required? | <Choose Value> | #REF!
6.8 | Does experience of the new working procedures or techniques exist? | <Choose Value> | #REF!
6.9 | What is the extent of end users knowledge of the application? | <Choose Value> | #REF!
Business Process |  |  | #REF!

## 7. Business Requirements
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
7 | Business Requirements | Value | Severity
7.1 | Is there a real business implementation deadline? | <Choose Value> | #REF!
7.2 | The system being built will replace the current: | <Choose Value> | #REF!
7.3 | What is the current attitude of the users towards the project? | <Choose Value> | #REF!
7.4 | What is the probability that the requirement specification will be changed? | <Choose Value> | #REF!
7.5 | How involved and committed are managers of the end user personnel? | <Choose Value> | #REF!
7.6 | Is the steering committee familiar with the client's activities and working practices? | <Choose Value> | #REF!
Business Requirements |  |  | #REF!

## 8. Cross Organization
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
8 | Cross-Organizational Topics | Value | Severity
8.1 | What is risk assessment Severity of current projects that this project depends on? | <Choose Value> | #REF!
8.2 | What is the geographical split of the project? | <Choose Value> | #REF!
8.3 | How many user departments are contributing to the project? | <Choose Value> | #REF!
8.4 | How many different client organizational units e.g. departments, divisions etc have responsibility for the system? | <Choose Value> | #REF!
8.5 | How many people will be using the system once it becomes operational? | <Choose Value> | #REF!
8.6 | How many organizational units will be involved when the system is live? | <Choose Value> | #REF!
8.7 | If the application will affect third parties eg. customers, suppliers or agents etc. has their involvement been taken into consideration? | <Choose Value> | #REF!
Cross-Organizational Topics |  |  | #REF!

## 9. Technology - Hardware
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
9 | Technology - Hardware | Value | Severity
9.1 | Are there any options to using new equipment or a new network that would still enable the system to function correctly? | <Choose Value> | #REF!
9.2 | Where will new equipment be required for the project or live system? | <Choose Value> | #REF!
9.3 | Where will unfamiliar equipment be required? | <Choose Value> | #REF!
9.4 | Where will equipment be required that is a new product for the supplier? | <Choose Value> | #REF!
9.5 | How many new suppliers will need to be contacted during the project? | <Choose Value> | #REF!
9.6 | The system will require network connections from the systems computer to | <Choose Value> | #REF!
9.7 | Where does expertise of the new network reside? Use the lower risk if more than one applicable? | <Choose Value> | #REF!
9.8 | How satisfactory will the support from the supplier of the system be? | <Choose Value> | #REF!
Technology - Hardware |  |  | #REF!

## 10. Technology - Software
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
10 | Technology - Software | Value | Severity
10.1 | Where does experience in the intended programming language (s) reside? select the lower risk if more than one is applicable | <Choose Value> | #REF!
10.2 | Which system software is new to the project team? Specify Other________________ | <Choose Value> | #REF!
10.3 | Is the system software a new release/version? | <Choose Value> | #REF!
10.4 | How many new suppliers will be needed for the system software? | <Choose Value> | #REF!
10.5 | Will ready-made packaes be used for application software? | <Choose Value> | #REF!
10.6 | Will the package require changes or additions? | <Choose Value> | #REF!
10.7 | How many users of the packaged software are there in this country? | <Choose Value> | #REF!
10.8 | What experience have clients of the supplier had in using a similar system or equipment? | <Choose Value> | #REF!
10.9 | How satisfactory will the support from the supplier of the system be? | <Choose Value> | #REF!
10.10 | Will fourth generation application facilities be used eg. graphics or report generators etc? | <Choose Value> | #REF!
Technology - Software |  |  | #REF!

## 11. Project Specific
Client: | ABC Corp | Project: | Alpha Project
Prepared By: | Mr PM | Date: | May 15 2007
6 | Project Specific | Value | Severity | Max Score
Project Specific Total |  |  | 0
Common IT Project Risk Factors (Not specifically identified in Worksheets 1 - 5)
1 | Data Complexity
2 | Scope or requirements uncertainty
3 | Stringent performance requirements
4 | Stringent acceptance criteria
5 | Leading edge, unreliable, or unproven technology
6 | Uniqueness
7 | Project Manager not full time
8 | Inflexible deadlines
9 | Scarce funds, funds from multiple sources
10 | Team over-specialized
11 | Opposition
12 | Reliance on others
13 | Business or technical standards not available
14 | Tools not available
15 | Over-specification (of function, security, generality, expandability, documentation)
16 | Volatile business area, many reorganizations
17 | Estimates not credible
18 | Benefits oversold, or not credible
19 | Stringent contract conditions (payment terms, cancellation options, liability, etc.)
20 | System introduces new concepts, making existing knowledge obsolete)
21 | Very many stakeholders, weak commitment
22 | Major changes to central organization structure
23 | System conflicts with personal reward systems, does not support personal interests
24 | Widespread apathy - 'just tell me what to do'

## 12. Risk Calculation
Client: | ABC Corp |  | Project: | Alpha
Prepared By: | Mr PM |  | Date: | May 1 2007
Risk Calculation
Group | 1. Size and scope | 2. IT Tools & Methods | 3. Project Organization | 4. Project Management | 5. Project operating conditions | 6. Business Process | 7. Business Requirements | 8. Cross Organization | 9. Technology - Hardware | 10. Technology - Software | 11. Project Specific | TOTAL PROJECT
Group Total # | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF!
Maximum Possible | 108 | #REF! | 121 | 87 | 33 | 116 | #REF! | #REF! | #REF! | #REF! | 0 | #REF!
Group Percentage Maximum Possible | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF!
Risk Indicator | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | n/a | #REF!
> 70% | Red
>40%, <70% | Yellow
< 40% | Green
The Maximum Possible numbers in the "blue" coded cells are reduced automatically if certain questions are answered as Not Applicable. These questions and the amount subtracted from the relevant groups' Maximum Possible figures are shown below.
Question | 2.1
Subtract | 9
Question | 9.7 | 9.1 | 10.6 | 10.7 | 10.8 | 10.9
Subtract | 12 | 12 | 20 | 9 | 25 | 12
Question | 7.6 | 8.7
Subtract | 9 | 12
7 | Other points to consider
There may be other risks not identified in the above questions. If the standard risk assessment is not to be carried out then these further risks should be documented eg. Quality of estimates, Mid-way start etc.

## Reference Data (hidden)
Reference Data - Do Not Change
Question | Values | Scores | Impact | Max Score | Question | Values | Scores | Impact | Max Score | Question | Values | Scores | Impact | Max Score | Question | Values | Scores | Impact | Max Score | Question | Values | Scores | Impact | Max Score | Question | Values | Scores | Impact | Max Score | Question | Values | Scores | Impact | Max Score | Question | Values | Scores | Impact | Max Score | Question | Values | Scores | Impact | Max Score | Question | Values | Scores | Impact | Max Score
1.1 | <Choose Value> | 0 | 5 |  | 2.1 | <Choose Value> | 0 | 3 |  | 3.1 | <Choose Value> | 0 | 5 |  | 4.1 | <Choose Value> | 0 | 5 |  | 5.1 | <Choose Value> | 0 | 3 |  | 6.1 | <Choose Value> | 0 | 5 |  | 7.1 | <Choose Value> | 0 | 4 |  | 8.1 | <Choose Value> | 0 | 5 |  | 9.1 | <Choose Value> | 0 | 3 |  | 10.1 | <Choose Value> | 0 | 3
| 1 - 100 | 0 | 5 |  |  | Not Applicable | 0 | 3 |  |  | 0 - 20% | 0 | 5 |  |  | Considerable | 0 | 5 |  |  | None | 0 | 3 |  |  | 51 - 100% | 0 | 5 |  |  | No | 0 | 4 |  |  | No dependents | 0 | 5 |  |  | Not applicable | 0 | 3 |  |  | All project team | 0 | 3
| 101 - 500 | 1 | 5 |  |  | Minor | 1 | 3 |  |  | 21 - 40% | 1 | 5 |  |  | Reasonable | 1 | 5 |  |  | Minor | 1 | 3 |  |  | 25 - 50% | 1 | 5 |  |  | Yes | 4 | 4 | 16 |  | Low risk only | 1 | 5 |  |  | Yes | 0 | 3 |  |  | Most of the project team | 1 | 3
| 501 - 1000 | 2 | 5 |  |  | Reasonable | 2 | 3 |  |  | 41 - 60% | 2 | 5 |  |  | Minimal | 2 | 5 |  |  | Reasonable | 2 | 3 |  |  | 0 - 25% | 2 | 5 | 10 | 7.2 | <Choose Value> | 0 | 5 |  |  | High risks | 3 | 5 | 15 |  | Yes, but with lower performance | 2 | 3 |  |  | Elsewhere in the company | 2 | 3
| 1001 + | 4 | 5 | 20 |  | Major changes | 3 | 3 | 9 |  | 61 - 100% | 3 | 5 | 15 |  | None | 3 | 5 | 15 |  | High | 3 | 3 | 9 | 6.2 | <Choose Value> | 0 | 5 |  |  | IT System | 0 | 5 |  | 8.2 | <Choose Value> | 0 | 2 |  |  | No | 4 | 3 | 12 |  | Outside the company | 3 | 3 | 9
1.2 | <Choose Value> | 0 | 4 |  | 2.2 | <Choose Value> | 0 | 3 |  | 3.2 | <Choose Value> | 0 | 5 |  | 4.2 | <Choose Value> | 0 | 5 |  | 5.2 | <Choose Value> | 0 | 3 |  |  | None | 0 | 5 |  |  | Manual System | 1 | 5 |  |  | One site | 0 | 2 |  | 9.2 | <Choose Value> | 0 | 3 |  | 10.2 | <Choose Value> | 0 | 4
| 0 - 4 | 0 | 4 |  |  | Minor | 0 | 3 |  |  | Satisfactory | 0 | 5 |  |  | Considerable | 0 | 5 |  |  | Mainly | 0 | 3 |  |  | Minor | 1 | 5 |  |  | Lack of system | 3 | 5 | 15 |  | 2 - 3 sites | 1 | 2 |  |  | Not applicable | 0 | 3 |  |  | None | 0 | 4
| 5 - 12 | 1 | 4 |  |  | Reasonable | 1 | 3 |  |  | Acceptable | 1 | 5 |  |  | Reasonable | 1 | 5 |  |  | Partially | 1 | 3 |  |  | Reasonable | 2 | 5 |  | 7.3 | <Choose Value> | 0 | 5 |  |  | 3 or more sites | 2 | 2 | 4 |  | IT Computer room | 2 | 3 |  |  | Database | 3 | 4
| 13 + | 3 | 4 | 12 |  | Major changes | 3 | 3 | 9 |  | Bad | 2 | 5 |  |  | Minimal | 2 | 5 |  |  | Few | 2 | 3 | 6 |  | Major | 3 | 5 |  |  | Positive | 0 | 5 |  | 8.3 | <Choose Value> | 0 | 4 |  |  | User department | 3 | 3 | 9 |  | Communications | 3 | 4
1.3 | <Choose Value> | 0 | 4 |  | 2.3 | <Choose Value> | 0 | 3 |  |  | Very Bad | 3 | 5 | 15 |  | None | 3 | 5 | 15 | 5.3 | <Choose Value> | 0 | 3 |  |  | Total | 4 | 5 | 20 |  | Interested | 1 | 5 |  |  | 1 | 0 | 4 |  | 9.3 | <Choose Value> | 0 | 5 |  |  | Other | 3 | 4 | 12
| No | 0 | 4 |  |  | Excellent | 0 | 3 |  | 3.3 | <Choose Value> | 0 | 4 |  | 4.3 | <Choose Value> | 0 | 5 |  |  | Simple | 0 | 3 |  | 6.3 | <Choose Value> | 0 | 5 |  |  | Questionable | 2 | 5 |  |  | 2 | 1 | 4 |  |  | Not applicable | 0 | 5 |  | 10.3 | <Choose Value> | 0 | 3
| Yes | 3 | 4 | 12 |  | Good | 1 | 3 |  |  | Yes | 0 | 4 |  |  | Considerable | 0 | 5 |  |  | Involved | 2 | 3 |  |  | None | 0 | 5 |  |  | Negative | 3 | 5 | 15 |  | 3+ | 2 | 4 | 8 |  | IT Computer room | 2 | 5 |  |  | No | 0 | 3
1.4 | <Choose Value> | 0 | 4 |  |  | Acceptable | 2 | 3 |  |  | Limited time | 2 | 4 |  |  | Reasonable | 1 | 5 |  |  | Complicated | 3 | 3 |  |  | Minor | 1 | 5 |  | 7.4 | <Choose Value> | 0 | 3 |  | 8.4 | <Choose Value> | 0 | 5 |  |  | User department | 3 | 5 | 15 |  | Yes | 2 | 3 | 6
| No | 0 | 4 |  |  | Poor | 3 | 3 | 9 |  | No | 4 | 4 | 16 |  | Minimal | 2 | 5 |  |  | Highly Complicated | 4 | 3 | 12 |  | Reasonable | 2 | 5 |  |  | Zero | 0 | 3 |  |  | 1 | 0 | 5 |  | 9.4 | <Choose Value> | 0 | 5 |  | 10.4 | <Choose Value> | 0 | 5
| Yes | 3 | 4 | 12 | 2.4 | <Choose Value> | 0 | 5 |  | 3.4 | <Choose Value> | 0 | 5 |  |  | None | 3 | 5 | 15 | 5.4 | <Choose Value> | 0 | 2 |  |  | Major | 3 | 5 | 15 |  | Small | 1 | 3 |  |  | 2+ | 4 | 5 | 20 |  | Not applicable | 0 | 5 |  |  | None | 0 | 5
1.5 | <Choose Value> | 0 | 3 |  |  | Yes | 0 | 5 |  |  | Full time | 0 | 5 |  | 4.4 | <Choose Value> | 0 | 5 |  |  | No | 0 | 2 |  | 6.4 | <Choose Value> | 0 | 3 |  |  | Medium | 2 | 3 |  | 8.5 | <Choose Value> | 0 | 2 |  |  | IT Computer room | 2 | 5 |  |  | 1 - 3 | 1 | 5
| Not Applicable | 0 | 3 |  |  | Only IT support | 2 | 5 |  |  | Part time | 1 | 5 |  |  | Yes | 0 | 5 |  |  | Minor | 1 | 2 |  |  | No | 0 | 3 |  |  | Large | 3 | 3 | 9 |  | 1 - 20 | 0 | 2 |  |  | User department | 3 | 5 | 15 |  | 3+ | 3 | 5 | 15
| Satisfactory | 1 | 3 |  |  | Not Applicable | 3 | 5 | 15 |  | Not at all | 3 | 5 | 15 |  | No | 3 | 5 | 15 |  | Reasonable | 2 | 2 |  |  | Yes, No training | 1 | 3 |  | 7.5 | <Choose Value> | 0 | 5 |  |  | 21 - 50 | 1 | 2 |  | 9.5 | <Choose Value> | 0 | 5 |  | 10.5 | <Choose Value> | 0 | 2
| Innsufficient | 2 | 3 |  | 2.5 | <Choose Value> | 0 | 3 |  | 3.5 | <Choose Value> | 0 | 5 |  | 4.5 | <Choose Value> | 0 | 3 |  |  | Major demands | 3 | 2 | 6 |  | Yes, training | 3 | 3 | 9 |  | Fully | 0 | 5 |  |  | 51 + | 2 | 2 | 4 |  | None | 0 | 5 |  |  | Totally | 0 | 2
| Overdue | 3 | 3 | 9 |  | Yes | 0 | 3 |  |  | In depth | 0 | 5 |  |  | Considerable | 0 | 3 | [5 empty] | 33 | 6.5 | <Choose Value> | 0 | 3 |  |  | Adequately | 1 | 5 |  | 8.6 | <Choose Value> | 0 | 2 |  |  | 1 - 3 | 1 | 5 |  |  | Mainly | 1 | 2
1.6 | <Choose Value> | 0 | 1 |  |  | Mainly | 1 | 3 |  |  | Concepts only | 1 | 5 |  |  | Reasonable | 1 | 3 | [7 empty] | None | 0 | 3 |  |  | Hardly | 2 | 5 |  |  | 1 | 0 | 2 |  |  | 3+ | 3 | 5 | 15 |  | Partly | 2 | 2
| Not Applicable | 0 | 1 |  |  | Partially | 2 | 3 |  |  | Minimal or none | 3 | 5 | 15 |  | Minimal | 2 | 3 | [7 empty] | Minor | 1 | 3 |  |  | Not | 3 | 5 | 15 |  | 2 - 3 | 1 | 2 |  | 9.6 | <Choose Value> | 0 | 4 |  |  | No | 3 | 2 | 6
| Satisfactory | 0 | 1 |  |  | No | 3 | 3 | 9 | 3.6 | <Choose Value> | 0 | 5 |  |  | None | 3 | 3 | 9 | [6 empty] | Reasonable | 2 | 3 |  | 7.6 | <Choose Value> | 0 | 3 |  |  | 3+ | 2 | 2 | 4 |  | None other | 0 | 4 |  | 10.6 | <Choose Value> | 0 | 5
| Minor Difference | 1 | 1 |  | 2.6 | <Choose Value> | 0 | 3 |  |  | No | 0 | 5 |  | 4.6 | <Choose Value> | 0 | 3 | [7 empty] | Major demands | 3 | 3 | 9 |  | Not Applicable | 0 | 3 |  | 8.7 | <Choose Value> | 0 | 3 |  |  | Telephone Link | 1 | 4 |  |  | Not applicable | 0 | 5
| Major Difference | 2 | 1 | 2 |  | Satisfactory | 0 | 3 |  |  | Yes | 5 | 5 | 25 |  | Considerable | 0 | 3 | [6 empty] | 6.6 | <Choose Value> | 0 | 5 |  |  | Fully | 0 | 3 |  |  | Not applicable | 0 | 3 |  |  | A like computer | 2 | 4 |  |  | No | 0 | 5
1.7 | <Choose Value> | 0 | 2 |  |  | Adequate | 1 | 3 |  | 3.7 | <Choose Value> | 0 | 5 |  |  | Reasonable | 1 | 3 | [7 empty] | Wide | 0 | 5 |  |  | Adequately | 1 | 3 |  |  | Yes | 1 | 3 |  |  | Different computer | 4 | 4 | 16 |  | Minor Change | 1 | 5
| Mainly Our staff | 0 | 2 |  |  | Restrictive | 2 | 3 |  |  | Yes | 0 | 5 |  |  | Minimal | 2 | 3 | [7 empty] | Some | 1 | 5 |  |  | Hardly | 2 | 3 |  |  | Partly | 2 | 3 |  | 9.7 | <Choose Value> | 0 | 3 |  |  | Major Change | 2 | 5
| Evenly divided | 1 | 2 |  |  | Unsatisfactory | 3 | 3 | 9 |  | To some extent | 1 | 5 |  |  | None | 3 | 3 | 9 | [6 empty] | None | 3 | 5 | 15 |  | Not | 3 | 3 | 9 |  | No | 4 | 3 | 12 |  | Not applicable | 0 | 3 |  |  | New program code | 4 | 5 | 20
| Few our staff | 2 | 2 | 4 | 2.7 | <Choose Value> | 0 | 5 |  |  | No | 2 | 5 | 10 | 4.7 | <Choose Value> | 0 | 3 | [6 empty] | 6.7 | <Choose Value> | 0 | 5 | [5 empty] | 79 |  |  |  |  | 67 |  | Project team | 1 | 3 |  | 10.7 | <Choose Value> | 0 | 3
1.8 | <Choose Value> | 0 | 4 |  |  | Yes | 0 | 5 |  | 3.8 | <Choose Value> | 0 | 5 |  |  | Yes | 0 | 3 | [7 empty] | None | 0 | 5 | [12 empty] | Elsewhere in Our | 2 | 3 |  |  | Not applicable | 0 | 3
| 0 | 0 | 4 |  |  | Mainly | 1 | 5 |  |  | No | 0 | 5 |  |  | Mainly | 1 | 3 | [7 empty] | 1 | 1 | 5 | [12 empty] | Network supplier | 4 | 3 | 12 |  | 5+ | 0 | 3
| 1 - 2 | 1 | 4 |  |  | Partially | 2 | 5 |  |  | Reasonable | 1 | 5 |  |  | Partially | 2 | 3 | [7 empty] | 2+ | 3 | 5 | 15 | [10 empty] | 9.8 | <Choose Value> | 0 | 3 |  |  | 3 - 5 | 1 | 3
| 3 - 5 | 2 | 4 |  |  | No | 3 | 5 | 15 |  | Yes | 2 | 5 | 10 |  | No | 3 | 3 | 9 | [5 empty] | 6.8 | <Choose Value> | 0 | 2 | [12 empty] | Not applicable | 0 | 3 |  |  | 1 - 2 | 2 | 3
| 6 - 9 | 3 | 4 |  | 2.8 | <Choose Value> | 0 | 4 | [5 empty] | 121 |  |  |  |  | 87 | [6 empty] | With users | 0 | 2 | [12 empty] | Good | 1 | 3 |  |  | 0 | 3 | 3 | 9
| 10 + | 4 | 4 | 16 |  | Yes | 0 | 4 | [17 empty] | System suppliers | 2 | 2 | [12 empty] | Reasonable | 2 | 3 |  | 10.8 | <Choose Value> | 0 | 5
1.9 | <Choose Value> | 0 | 2 |  |  | Mainly | 1 | 4 | [17 empty] | No | 4 | 2 | 8 | [11 empty] | Bad or unknown | 4 | 3 | 12 |  | Not applicable | 0 | 5
| Not applicable | 0 | 2 |  |  | Partially | 2 | 4 | [16 empty] | 6.9 | <Choose Value> | 0 | 5 | [15 empty] | 106 |  | Good | 0 | 5
| Yes | 1 | 2 |  |  | No | 3 | 4 | 12 | [16 empty] | In-depth | 0 | 5 | [17 empty] | unknown | 3 | 5
| Partly | 2 | 2 |  | 2.9 | <Choose Value> | 0 | 5 | [17 empty] | Concepts only | 1 | 5 | [17 empty] | Bad | 5 | 5 | 25
| No | 3 | 2 | 6 |  | Majority high | 0 | 5 | [17 empty] | Minimal or none | 3 | 5 | 15 | [15 empty] | 10.9 | <Choose Value> | 0 | 3
1.1 | <Choose Value> | 0 | 5 |  |  | Certain Lacking | 1 | 5 | [20 empty] | 116 | [16 empty] | Not applicable | 0 | 3
| 1 - 5 | 0 | 5 |  |  | Many lacking | 3 | 5 | 15 | [36 empty] | Good | 1 | 3
| 6 - 10 | 1 | 5 | [5 empty] | 102 | [36 empty] | Reasonable | 2 | 3
| 11 - 15 | 2 | 5 | [42 empty] | Bad or unknown | 4 | 3 | 12
| 16 + | 3 | 5 | 15 | [40 empty] | 10.1 | <Choose Value> | 0 | 2
|  |  |  | 108 | [41 empty] | No | 0 | 2
[46 empty] | Only one | 1 | 2
[46 empty] | More than one | 3 | 2 | 6
120